IEEE Foundation Grant Final Report

Regular and timely reports are required from recipients of grants from the IEEE Foundation General Fund, the IEEE Life Member Fund, or the IEEE Humanitarian Technology Fund.   Please read the guidelines for project reports available on the IEEE Foundation web site before completing this form.   The maximum number of characters (including any spaces) for each entry is specified and cannot be exceeded.  

If you have questions regarding the information required for any section of this form, please contact the IEEE Foundation by email at foundation-office@ieee.org.

Type your answers in the grey shaded boxes. Use the “TAB” key to navigate to the next field.  You must provide an answer to every question.

| Date Submitted: | 10-Aug-2015 |
| --- | --- |

(dd-MMM-yyyy)

Section 1:	Identify Your Project

| 1.1 Grant Identification Number: | 2014-025HTF |
| --- | --- |

1.2	Enter the Project Title (up to 50 characters)

Ghanaian Virtual Library for Universities"

Section 2:	Identify Yourself.

2.1	Your Contact Details:

| Title: |  | First Name: | Emmanuel | Last Name: | Dzadeyson |
| --- | --- | --- | --- | --- | --- |
| E-mail Address: |  |  | rirsgh@gmail.com |  |  |
| Telephone Number: |  |  | 0233544992757 |  |  |
| Mailing Address: |  |  | P.O. Box 191 Kasoa Central Region Ghana |  |  |

2.2	If there are any changes to your project team, please provide details and an explanation for the changes. (up to 300 characters)

No Change

Section 3:	Please provide the final report for your grant in the following sections.

Please refer to your grant application when you are completing the following sections.

3.1	Explain what you have achieved with your project.  (up to 1500 characters)

|  | The study have achieved by finding that Higher Educational Institutions in Ghana lack current and up to date books, journals and other learning materials Higher Educational Institutions are at different start-up points with different missions, priorities, needs and focus Given the limited funding available to academic libraries in Ghana, We also find out that it is obvious that scholars and students can only access a small portion of the information available in their disciplines. We have visited 57 Universities and Higher Education Institutions, centres and agencies of higher learning, research and development. A Ghanaian Virtual Library consultuim also has been established as part of our achiement. Thus, with the escalating costs of information materials and dwindling allocation of funds to academic institutions a judicious balance must be made to ensure that users of academic libraries in Ghana have access to relevant, appropriate information in their fields of interest. This can only be possible if libraries lay more emphasis on access rather than ownership. The study serves as a useful guide to developing and deploying solutions aimed at providing easy, fast, economical and remote, on-line or CD ROMbased,access to National and international content for education and research in the face of the dwindling per capita income. It will also serve as an avenue that will enable us to leap frog into the ICT age, therefore enabling Ghana to bridge the digital divide |
| --- | --- |

3.2	Detail the completion of your project in terms of the steps and projected dates that you provided in your application.  You may have modified some dates – please use the actual ones and explain any changes. (up to 1500 characters)

|  | 1 Day Stakeholders Meeting on Ghanaian Virtual Library for Universities and Higher Institutions organized on (6th January 2015). This event brings together stakeholders from the academia and the private sector. Recommendations were made from various Universities and organizations on structure for the Virtual Library and most agreed on decentralized system. Also a central coordinating body was established and called the Virtual Library Consortium. The Virtual Library Consortium is the coordinating body that will act as the regulator and facilitator of the Virtual Library Stakeholders. Strategic formulation Meeting for Ghanaian Virtual Library for Universities and Higher Institutions was organized on (31st January 2015) the event made up with various participants presenting papers. The participant provided with an implementation schedule for the development of a Virtual Library for the universities and Institutions of Higher Education. They also draw up a range of appropriate scalable implementation modules and strategies that various Institutions of Higher Education can adopt depending on their circumstances. A lot of people seen were specialist from Educational sector and some telecommunications specialist Formulation of a national generated strategy meeting on Ghanaian Virtual Library for Universities and Higher Institutions was organized on (4th t June 2015) Institutions were encouraged to partner with private sector, Cyber-cafes, Internet Service Providers (ISP). |
| --- | --- |

3.3	Detail how your project has been successful using the measures you described in your application form.  (up to 800  characters)

|  | The study has been successful in collaboration and involvement of specialist in the libraries and information management System, Telecommunication specialist, Higher Education specialist, both System Hard and Software specialist with a closed relation with the stakeholders which also involved in stakeholders meetings , in particular, the National Librarian, Vice-Chancellors of the Universities, librarians of universities, the National ICT Institute and the Ghanaian, experts of the national Libraries has made a successful preparation of the feasibility study report for Ghana. The specialist also visited 57 universities and higher institutions for data collection and interviews. |
| --- | --- |

3.4	If your project will result in an ongoing activity after the project is completed, explain what is being done to ensure its continuity. (up to 800 characters)

|  | The feasibility study has adopted the implementation of Ghanaian Virtual Libarary Consultuim which will be implementing the project after the grant project end. |
| --- | --- |

3.5	Describe how IEEE members or IEEE Organizational Units or others could benefit through the replication or extension of this project. (up to 1500 characters)

|  | The team of expect in the study are ready to help any organization who would like to replicate the project. Rural Integrated Relief Service-Ghana and his team members are ready to partner with the IEEE members or IEEE Organization unit to do so. |
| --- | --- |

3.6	Please view this example final financial statement.  Provide a Final Financial Statement for your project, showing the current status of all income and expenses, including all sources and amounts of funding.  Please refer to the project budget that was approved by the IEEE Foundation. Enter your financial data on the form provided below.

Note:	Your report will NOT be accepted if the Final Financial Statement is not provided.

GRANT FINAL FINANCIAL STATEMENT

| GRANT IDENTIFICATION NUMBER: | 2014-025HTF |
| --- | --- |

| PROJECT TITLE: | Ghanaian Virtual Library for Universities" |
| --- | --- |

List the items and amounts in the appropriate columns.  All amounts must be shown in US Dollars.  Click on the shaded boxes to type your information.

| INCOME |  |  | EXPENSES |  |  |
| --- | --- | --- | --- | --- | --- |
| Source of Income | Income from Other Sources (in US Dollars) | Project Income (in US Dollars) | Details of Project Expenses | Expenses paid from IEEE Foundation Grant (in US Dollars) | Expenses Paid with Other Funding (in US Dollars) |
| Grant Approved by IEEE Foundation |  | $9,700 | 1 System, Hard and Software Specialist | $1,000 | $600 |
| Total Income from Other Sources |  | $1,800 | 1 Libraries and information management Specialist | $1,400 |  |
| Details of IEEE Foundation Grant Payments: |  |  | 1 Telecommunications Specialist | $700 | $1,000 |
|  |  |  | 1 Higher Education Specialist | $1,000 |  |
|  |  |  | Production and Publication of the Feasibility Study Rep | $800 |  |
|  |  |  | 1 day meeting various stakeholders | $1,000 | $200 |
|  |  |  | stragegic formulation metting | $800 |  |
|  |  |  | Formulationof a national generated strategy meeting | $1,000 |  |
|  |  |  | 1 laptop with internet connetivity | $1,300 |  |
|  |  |  | Production of the final Report | $700 |  |
| Total Income from IEEE Foundation | $4,850 |  |  |  |  |
| Balance Remaining of IEEE Foundation Grant | $4,850 |  | Total Expenses (IEEE Foundation Grant) | $9,700 |  |
| Total Project Income | $6,650 |  | Total Other Expenses |  | $1,800 |
| Balance Remaining of Total Project Income | 00 |  | Total Project Expenses | $11,500 |  |

STEP 5.	A copy for your records.

Please PRINT and/or SAVE a copy of this form for your own records.

STEP 6.	Declarations

By submitting this Final Report to the IEEE Foundation, I, [ Emmanuel] [Dzadeyson], certify that:

1)	I am the grantee, or an authorized representative of the grantee;

2)	To the best of my knowledge and belief, the data in the Report is correct and all the outlays were made in accordance with the Grant Agreement;

3)	 that payment is due and has not been previously requested; and

4)	the grantee is complying with the representations, terms and conditions of the grant.

STEP 7:	Submit your Final Report

After completing every field on this form, SAVE the form as either a Microsoft Word document or PDF file and send it as an e-mail attachment to foundation-office@ieee.org with “IEEE Foundation Final Report” as the “Subject” line of your e-mail message.