**PERIODIC ACTIVITY REPORT BY RURAL AID CAMEROON “RAC”**

**Reporting Period: 2014-2016 – January to December Annually**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Code** | **Planned Activity** | **Objective** | **Results** | **Difficulties** **Encountered** |
| **01** | **Education & Training** | To reduce Illiteracy rate of rural populations and build their capacities in sustainable development | 10 rural communities were reached and sensitized04 Training Workshops and Seminars were organized and run on Involvement of local inhabitants on Income-generating activities | Some of our target communities were not reached due to insufficient resources.Some others were left out due to poor earth road conditions caused by prolonged rains. |
| **02** | **Youths & Women in Development** | To socially and economically empower rural youths and women in sustainable development | 05 Youth and 10 Women Groups were created and trained on the involvement of youths and women in the process of sustainable development | Only 45% of the expected results were achieved due to the non-commitment of some youths and women |
| **03** | **Social Welfare** | To create a synergy of Care and Support to Orphaned and Vulnerable Children “OVC”.To access disabled children to economic empowerment | 04 Orphanages have been reached 08 communities and consulted for needs assessment.Two Sub Divisions were reached to assess needs of children with disabilities | We have only succeeded to negotiate for and acquire 45 out of 80% envisaged international assistance in funding and humanitarian assistance |
| **04** | **Community Development** | To down-scale the level of underdevelopment in target rural communities | 12 communities out of 45 were reached through outreach education and sensitization.04 Bore-hole projects were initiated and executed.03 Community halls were constructed. | The envisaged 70% success was not attained due to unavailability of external funding to implement identified and feasible community projects which are their actual needs. |
| **05** | **Sustainable Agriculture**Cassava Production & Processing | 1) To promote gender equality and economic empowerment of rural women’s groups.2) To boost production and improve quality productivity using the Organic Approach | 10 rural communities have been sensitized wherein 20 Groups made up of under-privileged and marginalized Single Mothers, Widows, Unemployed Women have been provided adaptive technology and assisted with seed capital | Rural Groups have experienced a lot of dumping of end products due poor farm-to-market roads and inaccessibility to distant market outlets. |

* **2 -**

**ANNUAL ACTIVITY REPORT BY RURAL AID CAMEROON “RAC”**

**Reporting Period: 2016 – 2018 – January to December Annually**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Code** | **Planned Activity** | **Objective** | **Results** | **Difficulties** **Encountered** |
| **01** | **Education & Training** | To reduce Illiteracy rate of rural populations and build their capacities in sustainable development | 1) 10 rural communities were reached and sensitized.2) 03 Training Workshops and Seminars were organized to build the capacities of local inhabitants on income-generation. | Some of our target communities were not reached due to insufficient resources. Some others were left out due to poor earth road conditions caused by prolonged rains. |
| **02** | **Social Welfare** | To create a synergy of Care and Support to Orphaned and Vulnerable Children “OVC” | 10 (ten) Orphanages have been reached in 20 communities and consulted for needs assessment | We have not yet succeeded in acquiring international assistance to finance social projects. |
| **03** | **Sustainable Agroforestry Campaign** | To assist rural farming Groups adopt strategic mechanisms to reverse the effects and impacts of climate change | 1) 07 schools were reached to initiate and form Agroforestry Clubs.2)14 rural and 6 urban communities were reached and trained on tree-planting and nursery-raising. | We encountered difficulties in providing nitrogen-fixing plant seeds to target communities. We equipped farmers with only 35% of the needed resources to enable them successfully implement tree-planting activities. |
| **04** | **Sustainable Agriculture** | 1) To promote soil-plant-crop-animal interaction farming system and secure value added agricultural production.2) To help create a synergy of animal and livestock production and conservation. for resource-generation (Reduction of Biodiversity Loss) | 1) 30%/35% of target mar-ginalized groups made up of Single Mothers, Widows, Unemployed Women and stakeholders were reached, educated, sensitized and assisted with seed funding and inputs.2) 10/20 Rural Community Groups were formed, sensitized , trained and assisted with start-up capital and breeds for micro projects take-off | There was but a 5% short fall emanated from the inadequate follow up skills of our Field Extension Worker and relative response/commitment of some local farming group members and stakeholders.Our NGO was not disposed of the expected resources to fully assist target rural groups. |
| **05** | **Quality & Appropriate Healthcare** | To construct modern toilet and shower bathrooms and provide modern medical equipment in 2 District Hospitals in 2 Divisions  | 02 District Hospitals were served with modern toilets and medical equipment | We encountered problems of transportation/movements due to travel by earth roads to reach target hospitals in rural areas |