## Sheet1
Forefront Uganda action plan from December 2019-April 2020
SN | Activities | imput | output | Outcome | Responsible persons | Date | Duration | Months
1 | working and updating weekly infobites | 4 hours preparing, computer, electricity | plan for the week developed | cordination of activities as per plan shedule, tracking what is done and not done is easy for the next planning | Founder/ Director | fed in the daily to-do list accordingly | 2 times a month | December
2 | Board formulation | Hire for motocycle, lunch allowance, staionary, printing organisation documents to present to board | potential board member identified | board member formed, Governance structure in place | Founder/Director ,lawyer, Board members | fed in the daily to-do list accordingly | 5 Days | December
3 | revisiting constitution | lunch ,Transport refund for board member,printing, stationary | proposed constituion revised together with the board | Constitution approved by the board as governing documents | Founder/Director ,lawyer, Board members | fed in the daily to-do list accordingly | 1 time | December
4 | social Media and website Update | Internet, electricity, laptop, content | 2 time a month website update and social media pages | websited and social media updated atleast twice a month | Founder/ Director | fed in the daily to-do list accordingly | 2 times a month | December
5 | updating Donor database | Internet, electricity, laptop, | updated weekly database for potential donors | identification of potential donors weekly | Founder/ Director | fed in the daily to-do list accordingly | weekly | December
6 | updating Donor database | Internet, electricity, laptop, | updated weekly database for potential donors | identification of potential donors weekly | Founder/ Director | fed in the daily to-do list accordingly | weekly | December
7 | Proposal wrting and development | Internet, electricity, laptop, phone, review team, recommendation letters, referrees | morethan 7 proposal develop per month | proposals develop and summited for funding request. | Founder/ Director | fed in the daily to-do list accordingly | 4 times | December
8 | Weekly Mentoreship support | transport, internet, call bundles, cell phone, computer | one weekly meetting done | consultation and planning for previous week | Kanthari Allumini and Founder/ Director | fed in the daily to-do list accordingly | 1 time | December
1 | working and updating weekly infobites | 4 hours preparing, computer, electricity | plan for the week developed | cordination of activities as per plan shedule, tracking what is done and not done is easy for the next planning | Founder/ Director | fed in the daily to-do list accordingly | Weekly | January
2 | social Media and website Update | Internet, electricity, laptop, content | 2 time a month website update and social media pages | websited and social media updated atleast twice a month | Founder/ Director | fed in the daily to-do list accordingly | 2 times a month | January
3 | updating donors database | Internet, electricity, laptop, | updated weekly database for potential donors | identification of potential donors weekly | Founder/ Director | fed in the daily to-do list accordingly | Weekly | January
4 | revisiting HRM policy with baord members | lunch ,Transport refund for board member,printing, stationary | proposed HRM policy revised together with the board | HRM policy approved by the board as management documents | Founder/Director ,lawyer, Board members | fed in the daily to-do list accordingly | 1 day | January
5 | Revisting and approving Financial Management policies | lunch ,Transport refund for board member,printing, stationary | Financial mgt policy revised together with the board | financial policy approved by the board as management documents | Founder/Director ,Charterd accountant, Board members | fed in the daily to-do list accordingly | 2 days | January
6 | Proposal wrting and development | Internet, electricity, laptop, phone, review team, recommendation letters, referrees | morethan 7 proposal develop per month | proposals develop and summited for funding request. | Founder/ Director | fed in the daily to-do list accordingly | 2 days | January
7 | Staff and volunteers sourcing | motocycle, airtime, lunch | potential volunteers and staffs identified | roles and responsibilities given to staffs and volunteers. | Founder/ Director | fed in the daily to-do list accordingly | 3 days | January
8 | Mentoreship support | transport, internet, call bundles, cell phone, computer | one weekly meetting done | consultation and planning for previous week | Kanthari Allumini and Founder/ Director | fed in the daily to-do list accordingly | weekly | January
9 | Board meeting | lunch ,Transport refund for board member,printing, stationary | 1 board meeting conducted for 2020 | policies , annual work plan, annual budget approved. | Founder/Director , Board members | fed in the daily to-do list accordingly | 1 day | January
10 | Monthly reporting to Kanthari | internet,computer, electricity | report for month prepared | reporting progress from previous plan and resheduling for the next month |  | fed in the daily to-do list accordingly | once | January
11 | staff training and development | statonary, computers, internet,refreshements | once a week training conducted for staffs. | improvement in the capacity of the staffs to executed their task | Founder/ Director | fed in the daily to-do list accordingly | every Friday | January
12 | weekly skype, wastsap calls with felow participants from kanthari | Internet, electricity, laptop, phone | Skype call made to atleast 4 fellows per month | best learning practise form fellows | Founder/ Director | fed in the daily to-do list accordingly | 2 times a month | Janauary
13 | meeting with beneficiaries groups | transport,printing,lunch,airtime | update on current situation, and feedback form beneficiairies | update on current situation, and feedback form beneficiairies | Founders/ Director | fed in the daily to-do list accordingly | 2 times | January
1 | working and updating weekly infobites | 4 hours preparing, computer, electricity | plan for the week developed | cordination of activities as per plan shedule, tracking what is done and not done is easy for the next planning | Founder/ Director | fed in the daily to-do list accordingly | Weekly | Febuary
2 | weekly skype, wastsap calls with felow participants from kanthari | Internet, electricity, laptop, phone | Skype call made to atleast 4 fellows per month | best learning practise form fellows | Founder/ Director | fed in the daily to-do list accordingly | 2 times a month | Febuary
3 | social Media and website Update | Internet, electricity, laptop, content | 2 time a month website update and social media pages | websited and social media updated atleast twice a month | Founder/ Director | fed in the daily to-do list accordingly | 2 times a month | Febuary
4 | updating donors database | Internet, electricity, laptop, | updated weekly database for potential donors | identification of potential donors weekly | Founder/ Director | fed in the daily to-do list accordingly | Weekly | Febuary
5 | Proposal wrting and development | Internet, electricity, laptop, phone, review team, recommendation letters, referrees | morethan 7 proposal develop per month | proposals develop and summited for funding request. | Founder/ Director | fed in the daily to-do list accordingly | Weekly | Febuary
6 | Mentoreship support | transport, internet, call bundles, cell phone, computer | one weekly meetting done | consultation and planning for previous week | Kanthari Allumini and Founder/ Director | fed in the daily to-do list accordingly | weekly | Febuary
7 | Monthly reporting to Kanthari | internet,computer, electricity | report for month prepared | reporting progress from previous plan and resheduling for the next month |  | fed in the daily to-do list accordingly | once | Febuary
8 | staff training and development | statonary, computers, internet,refreshements | once a week training conducted for staffs. | improvement in the capacity of the staffs to executed their task | Founder/ Director | fed in the daily to-do list accordingly | every Friday | Febuary
9 | meeting with beneficiaries groups | transport,printing,lunch,airtime | update on current situation, and feedback form beneficiairies |  | Founders/ Director | fed in the daily to-do list accordingly | 2 times | Febuary
1 | working and updating weekly infobites | 4 hours preparing, computer, electricity | plan for the week developed | cordination of activities as per plan shedule, tracking what is done and not done is easy for the next planning | Founder/ Director | fed in the daily to-do list accordingly | Weekly | March
2 | social Media and website Update | Internet, electricity, laptop, content | 2 time a month website update and social media pages | websited and social media updated atleast twice a month | Founder/ Director | fed in the daily to-do list accordingly | monthly | March
3 | Mentoreship support | transport, internet, call bundles, cell phone, computer | one weekly meetting done | consultation and planning for previous week | Kanthari Allumini and Founder/ Director | fed in the daily to-do list accordingly | weekly | March
4 | Proposal wrting and development | Internet, electricity, laptop, phone, review team, recommendation letters, referrees | morethan 7 proposal develop per month | proposals develop and summited for funding request. | Founder/ Director | fed in the daily to-do list accordingly | Weekly | March
5 | Monthly reporting to Kanthari | internet,computer, electricity | report for month prepared | reporting progress from previous plan and resheduling for the next month | Founder | fed in the daily to-do list accordingly | once | March
6 | staff training and development | statonary, computers, internet,refreshements | once a week training conducted for staffs. | improvement in the capacity of the staffs to executed their task | Founder/ Director | fed in the daily to-do list accordingly | every Friday | March
7 | meeting with beneficiaries groups | transport,printing,lunch,airtime | update on current situation, and feedback form beneficiairies | update on current situation, and feedback form beneficiairies | Founders/ Director | fed in the daily to-do list accordingly | 2 times | March
1 | working and updating weekly infobites | 4 hours preparing, computer, electricity | plan for the week developed | cordination of activities as per plan shedule, tracking what is done and not done is easy for the next planning | Founder/ Director | fed in the daily to-do list accordingly | Weekly | April
2 | social Media and website Update | Internet, electricity, laptop, content | 2 time a month website update and social media pages | websited and social media updated atleast twice a month | Founder/ Director | fed in the daily to-do list accordingly | monthly | April
3 | Mentoreship support | transport, internet, call bundles, cell phone, computer | one weekly meetting done | consultation and planning for previous week | Kanthari Allumini and Founder/ Director | fed in the daily to-do list accordingly | weekly | April
4 | Proposal wrting and development | Internet, electricity, laptop, phone, review team, recommendation letters, referrees | morethan 7 proposal develop per month | proposals develop and summited for funding request. | Founder/ Director | fed in the daily to-do list accordingly | Weekly | April
5 | Weekly Mentoreship support | transport, internet, call bundles, cell phone, computer | one weekly meetting done | consultation and planning for previous week | Kanthari Allumini and Founder/ Director | fed in the daily to-do list accordingly | 1 time | April
6 | Monthly reporting to Kanthari | internet,computer, electricity | report for month prepared | reporting progress from previous plan and resheduling for the next month |  | fed in the daily to-do list accordingly | once | April
7 | staff training and development | statonary, computers, internet,refreshements | once a week training conducted for staffs. | improvement in the capacity of the staffs to executed their task | Founder/ Director | fed in the daily to-do list accordingly | every Friday | April
8 | meeting with beneficiaries groups | transport,printing,lunch,airtime | I meeting conducted per month | update on current situation, and feedback form beneficiairies | Founders/ Director | fed in the daily to-do list accordingly | 2 times | April