AFRICAN WOMENS DIGNITY FOUNDATION AWDF

**THE ANNUAL STRATEGIC WORK PLAN FOR THE YEAR 2019**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **PROJECT** | **PROJECT OBJECTIVES** | **IN PUTS** | **TIME SCHEDULE** | **PERSON RESPONSIBLE** | **INDICATRORS.** |
| Art and Craft project | -To improve the production capacity of the women in art and craft by 75 percent. | -To solicit more funds to support women producing art and craft  -To train the female art and craft producers in different innovation skills.  -To organize trade exhibition and trade shows | From January to June 2019 | -The executive committee of AWDF  -Trainers qualified in art and craft | -Funds realized from sales of crafts and well wishers.  -More women trained and join the production industry of art and craft  -Through the trade shows wide market shall be realized from the community members and the tourists. |
| Mushroom and cultivation project | -To equip the rural and urban women how to produce mushroom for economic empowerment | -Training women in mushroom cultivation and processing process  -Avail mushroom processing facilities like mushroom spawns and substrates to the farmers. | March to December 2019 | -AWDF executive committee  -Soliciting for skilled personnel in mushroom cultivation | -More farmers trained.  -Enough cultivation processing facilities available.  -Increased production hence high income. |
| Sun flower growing and processing for women empowerment | -To help equip the rural women in different communities of Kasese district with appropriate knowledge and skills on sun flower growing and processing. | -Soliciting funds for traininng women in sun flower growing and processing  -Putting in place a training demonstration garden | June to December 2019 | -AWDF executive committee  -Qualified trained agronomists | -40 rural women shall have gained training and continue training other women.  -Demonstration farm shall be in place to train farmers practically. |
| Savings and credit project | -To improve and promote the savings culture among the members. | -Mobilization for more savings  -Increase on credit ranged by 40 percent | Continuous: January to December 2019 | -All members of AWDF | -Savings increased from currently 2,150,000 to 3,500,000 Ug shs  -Credit limit will have increased from 200,000 to 400,000 Ug Shs. |
| Capacity building | -To boost the capacity of the executive members and the staff for effective management and planning of the organization | -Training the executive committee and the staff in project planning and management.  -Training the treasurer in modern financial management skills  -Training the executive committee in effective monitoring and evaluation.  -Training all members of the organization in farm management skills. | January to November 2019 | -Executive committee  AWDF | -The executive committee shall execute their duties in a more technical manner and be capable to monitor and evaluate its project.  -All the members of the organization shall have attained knowledge on farm management. |