## Sheet1
Financial Report
Name of CBO:
Title of Project: |  | Strengthening Waste Management Systems (SWAMS)
Agreement No. |  | TIL-CB2-16-043-G
Periode: |  | June, 2017
Activities |  | Budgeted Amount | Spent this Period | Previous Cummulative expenditure | Expenditure Todate (Cummulative) | Budget balance left
|  | A | B | C | B+C | A-(B+C)
(i) | Personnel Costs
| Executive Director 20% | 567794 | 551000 |  | 551000 | 16794
| Accounts Assistant 30% | 567794 | 551000 |  | 551000 | 16794
| Project Officer 30% | 567794 | 551000 |  | 551000 | 16794
| Office Assistant 36% | 227118 | 200000 |  | 200000 | 27118
| MRA Personnel PAYE |  | 123750 |  | 123750 | -123750
| SUB TOTAL | 1930500 | 1976750 | 0 | 1976750 | -46250
(ii) | Direct Costs | 0
(a) | Output (1) Enhanced and reinforced capacity of citizens and local governance structures on their roles and the roles of the Council regarding the waste management services
Activity 1
1.1 | Conduct 1 Meeting with Urban Executive Committee to introduce the project and share responsibilities | 114700 |  | 0 | 0 | 114700
| DSA- for selected Participants | 62500 |  | 0 | 0 | 62500
| DSA – Facilitators/Governance expert/ Media | 2500 |  | 0 | 0 | 2500
| Stationery | 18800 |  | 0 | 0 | 18800
| Refreshments and snacks | 18900 |  | 0 | 0 | 18900
| Fuel Project team (mobilization and day of activity) | 12000 |  | 0 | 0 | 12000
1.2 | Conduct 1 training to 15 community based volunteers and 15 Opinion Leaders from the 2 wards on the project outputs how to manage the project | 181200 | 181200 |  | 181200 | 0
| Stationery/Training Manuals | 23100 |  | 0 | 0 | 23100
| 3 Proj Team + 30 Participants CBVEs lunch | 82500 |  | 0 | 0 | 82500
| Participants /CBVE travel Refunds | 18000 |  | 0 | 0 | 18000
| Refreshments and snacks 33 | 23100 |  | 0 | 0 | 23100
| Fuel | 12000 |  | 0 | 0 | 12000
| Venue hire | 15000 |  | 0 | 0 | 15000
| Communication (Airtime) | 5000 |  | 0 | 0 | 5000
| DSA facilitators/ Governance Expert | 2500 |  | 0 | 0 | 2500
|  |  |  | 0 | 0 | 0
1.3 | Conduct 4 focus group discussions with the citizens on rights and policies as regards to waste management in each of the 2 Wards | 419600 | 806350 |  |  | 419600
| Training Manuals per session for 20 selected | 56000 |  | 0 | 0 | 56000
| Lunch for 20 selected participants per session | 200000 |  | 0 | 0 | 200000
| Refreshments and snacks per session | 75600 |  | 0 | 0 | 75600
| Communication (Airtime) | 20000 |  | 0 | 0 | 20000
| DSA allowances for 2 facilitators per session | 20000 |  | 0 | 0 | 20000
| Fuel for a car | 48000 |  | 0 | 0 | 48000
1.4 | Conduct 1 training for 50 women and other 25 disadvantaged on their roles and rights in waste management | 342500 | 342500 |  | 342500 | 0
| Manuals, Writing pads and pens for 75 participants | 52500 |  | 0 | 0 | 52500
| Refreshments for 80 people (5 sessions) | 56000 |  | 0 | 0 | 56000
| Project fuel | 12000 |  | 0 | 0 | 12000
| Transport for 2 facilitators | 7000 |  | 0 | 0 | 7000
| Venue hire | 15000 |  | 0 | 0 | 15000
| DSA for 80 people | 200000 |  | 0 | 0 | 200000
1.5 | Conduct 2 Post election/ Evidence based performance assessment for elected representatives for the past 2 years by local citizens and media on the promises by the MP/ Councillors as regards to Waste management | 314000 | 314000 |  | 314000 | 0
| Stationery for the session for 40 participants | 56000 |  |  |  | 56000
| DSA for 38 participants | 190000 |  |  |  | 190000
| Transport refund for journalists | 14000 |  |  |  | 14000
| Venue hire | 30000 |  |  |  | 30000
| Project fuel | 24000 |  |  |  | 24000
1.6 | Lobby for formulation of effective laws and enforcement of regulations and influencing of by-laws (informal/formal) on grassroot waste management to enable citizens practice proper waste management | 772400 | 1112900 |  | 1112900 | -340500
| Transport for 22 participants | 52800 |  |  |  | 52800
| Print out materials on waste management by laws | 61600 |  |  |  | 61600
| DSA for 22 participants and 3 project officers | 250000 |  |  |  | 250000
| Project fuel | 48000 |  |  |  | 48000
| Taskforce Honoraria |  |  |  |  | 0
| Travel, stationery, refreshment and communication of 2 community based inspectors for 2 wards | 360000 |  |  |  | 360000
1.7 | Conduct 4 community awareness campaigns in each of the 2 Wards on responsibility of monitoring the waste management systems, resources and all rights issues. | 1756000 | 1724250 |  | 1724250 | 31750
| Refreshments for 3 project team and 3 volunteers | 86900 |  | 0 | 0 | 86900
| Project vehicle Fuel | 126000 |  | 0 | 0 | 126000
| Communication | 53000 |  | 0 | 0 | 53000
| Stationery for posters and letters | 100000 |  | 0 | 0 | 100000
| Vehicle Hire for carrying PA system equipment | 170000 |  | 0 | 0 | 170000
| Dances and drama | 255000 |  | 0 | 0 | 255000
| Hire PA system | 222500 |  | 0 | 0 | 222500
| Stakeholders DSA per session | 352600 |  | 0 | 0 | 352600
| Volunteers /Organising team Allowance (3) per session | 60000 |  | 0 | 0 | 60000
| Hire chairs | 80000 |  | 0 | 0 | 80000
| Production of T shirts on waste management | 250000 |  | 0 | 0 | 250000
| Distribution of newsletters and leaflets |  |  | 0 | 0 | 0
Output 2: Increased participation, dialogue between citizens, local governance structures, other stakeholders (media, CBOs, private sector) and the Blantyre City Council to improve waste management.
2.1 | Conduct 2 public debates in each of the 2 wards involving 2 councilos & 1 MP, 2 media and the 10 women groups representatives. The debates will provide responses to meet the citizens’ demands on waste management (Targeting 2000 women, 2000 men, 3000 youth) | 365500 | 311600 |  | 311600 | 53900
| DSA for 3 panelists and 3 elected representatives | 65000 |  | 0 | 0 | 65000
| Travel refund for 3 panelists | 45500 |  | 0 | 0 | 45500
| Refreshments for 20 selected participants | 70000 |  | 0 | 0 | 70000
| Project fuel | 60000 |  | 0 | 0 | 60000
| PA system hire | 80000 |  | 0 | 0 | 80000
| DSA for participants | 45000 |  | 0 | 0 | 45000
| Activity 2 |  |  | 0 | 0 | 0
2.2 | Conduct 3 interface meetings spearheaded by WDCs involving council, media, CBO's, Schools, private sector/ Companies) who are involved in waste disposal | 660200 | 576400 |  | 576400 | 83800
| Refreshments for 27 participants and 3 project staff | 105000 |  | 0 | 0 | 105000
| Project fuel | 60000 |  | 0 | 0 | 60000
| Venue Hire | 75000 |  | 0 | 0 | 75000
| Local Transport refund for 27 participants | 97200 |  | 0 | 0 | 97200
| DSA for 27 participants and 3 project staff | 300000 |  | 0 | 0 | 300000
| Communication for the event | 23000 |  | 0 | 0 | 23000
|  |  |  | 0 | 0 | 0
| Activity 3 |  |  | 0 | 0 | 0
2.3 | Conduct 5 Case Studies – Document 5 Ordinary Citizen’s stories as a result of poor waste management + experiences for results and lessons sharing. | 420000 | 312500 |  | 312500 | 107500
| Print out copies of case studies | 50000 |  | 0 | 0 | 50000
| Video production(documentary) cost | 120000 |  | 0 | 0 | 120000
| Project fuel | 60000 |  | 0 | 0 | 60000
| DSA allowances for 10 citizens being interviewed | 25000 |  | 0 | 0 | 25000
| DSA allowances for 3 project staff | 37500 |  | 0 | 0 | 37500
| Refreshment for 15 participants | 52500 |  | 0 | 0 | 52500
| Distribution of documentary to relevant stakeholders( Transport) | 25000 |  | 0 | 0 | 25000
| Collection of Ordinary Citizens stories | 40000 |  |  |  | 40000
| Travel cost | 10000 |  |  |  | 10000
| Activity 4 |  |  | 0 | 0 | 0
2.4 | Facilitate production of 3 newsletters (Quarterly) and 8, 000 leaflets concerning rights to waste management issues and recording of results from the evidence based performance assessment report | 675000 | 635000 |  | 635000 | 40000
| Produce of 1 of 3 news letters and duplication (100) | 390000 |  |  |  | 390000
| Production of 8000 leaf lets | 285000 |  | 0 | 0 | 285000
| Activity 5 | 0 |  | 0 | 0 | 0
2.5 | Conduct Quarterly community feed back meetings for evaluation and planning for improving of waste management and resources. | 475000 | 527050 |  | 527050 | -52050
| Communication | 11500 |  | 0 | 0 | 11500
| Print outs for 25 participants | 70000 |  | 0 | 0 | 70000
| Refreshments for 25 people | 91000 |  | 0 | 0 | 91000
| DSA for 25 people | 156500 |  | 0 | 0 | 156500
| Venue hire | 80000 |  | 0 | 0 | 80000
| Project fuel | 51000 |  | 0 | 0 | 51000
| DSA for Officials | 15000
| Activity 6 |  |  | 0 | 0 | 0
2.6 | Conduct Quarterly open days for information sharing and improving of waste management targeting 2000 women, 2000 men, 3000 youth | 1069250 | 1193450 |  | 1193450 | -124200
| DSA for 18 selected S/holders + 2 media | 300000 |  | 0 | 0 | 300000
| PA system hire | 120000 |  | 0 | 0 | 120000
| Refreshments for 20 participants | 84000 |  | 0 | 0 | 84000
| Guest speaker fuel refund | 28250 |  | 0 | 0 | 28250
| Exhibitions cost on waste management | 90000 |  | 0 | 0 | 90000
| 6 Solid waste management entrepreneurs DSA | 90000 |  | 0 | 0 | 90000
| Conduct Interface meeting on information sharing including position on By- Laws by The City Council. | 0 |  | 0 | 0 | 0
| Communication | 5000 |  | 0 | 0 | 5000
| Travel Refunds for WDCs | 23000 |  | 0 | 0 | 23000
| Refreshments for 22 people | 27300 |  | 0 | 0 | 27300
| Sitting Honoraria for City officials | 199000 |  | 0 | 0 | 199000
| DSA for Project Officials | 12500 |  | 0 | 0 | 12500
| DSA for Ward participants | 57500 |  | 0 | 0 | 57500
| Stationary + printouts+ airtime | 17700 |  | 0 | 0 | 17700
| Project fuel | 15000 |  | 0 | 0 | 15000
| Monitoring and Evaluation |  |  | 0 | 0 | 0
| Activity (i) |  |  | 0 | 0 | 0
3.1 | Conduct baseline survey to assess the governance issues and other needs of the community as regards to waste management (This will be done in collaboration with Tilitonse) |  |  | 0 | 0 | 0
| Activity (ii) |  |  | 0 | 0 | 0
3.2 | Conduct monitoring and evaluation by developing monitoring forms to be used for data collection and to document community progress. Umodzi shall conduct frequent monitoring, and end of period evaluation. | 752400 | 825200 |  | 825200 | -72800
| Project fuel for monthly field visits | 204000 |  | 0 | 0 | 204000
| Documentation /Documentary | 254800
| Stationery for reporting( Cartilage, A4 papers) | 140000 |  | 0 | 0 | 140000
| Refreshments for 3 project staff | 33600 |  | 0 | 0 | 33600
| DSA for 3 staff | 120000 |  | 0 | 0 | 120000
| Activity (iii) |  |  | 0 | 0 | 0
3.3 | Conduct project end evaluation. This will be done in collaboration with Tilitonse |  |  | 0 | 0 | 0
| Cost of project evaluation | 500000 | 260000 | 0 | 260000 | 240000
| Activity(iv) | 0 |  | 0 | 0 | 0
3.4 | Conduct auditing | 500000 |  | 0 | 0 | 500000
| Direct Costs Totals | 9317750 | 9122400 |  | 9122400 | 195350
(iii) | Indirect Costs
| Rentals (42% contribution) | 329460.7169 | 287400 |  | 287400 | 42060.7169
| Bank Charges | 104895.8524 | 94524.86 |  | 94524.86 | 10370.9924
| General Travel | 69000 | 69000 |  | 69000 | 0
| Travel to LL (4 Trips for 2 pple) | 82000 | 82000 |  | 82000 | 0
| Office supplies/ Sundries | 197676.4302 | 185747.12 |  | 185747.12 | 11929.3102
| Postage | 54763.6925 | 33000 |  | 33000 | 21763.6925
| Communication / internet | 234283.1765 | 200000 |  | 200000 | 34283.1765
| Procure 1 set Desk top computer | 406200 | 431050 |  | 431050 | -24850
| Procure of 1 laptop | 356200 | 350000 |  | 350000 | 6200
| procure 1 digital camera | 150000 | 120000 |  | 120000 | 30000
| Procure 1 project printer | 150000 | 145625 |  | 145625 | 4375
| Insurance for the procured assets | 53445.8496 | 0 | 0 | 0 | 53445.8496
| Indirect Costs totals | 2187925.7181 | 1998346.98 | 0 | 1998346.98 | 189578.7381
| GRAND TOTAL | 13436175.7181 | 13097496.98 |  | 13097496.98 | 338678.7381
0
Prepared by: James Kadembo |  |  | Date : 10th August, 2017
Checked by: Patricia Makobiri |  |  | Date : 10th August, 2017
Approved by: Munyaradzi Moffat |  |  | Date : 10th August, 2017
Reviwed by: ___________________________________ |  |  | Date :_____________________

## Sheet2
CASH BOOK | [9 empty] | CBO CASH BOOK
NAME OF CBO: KATENGEZA COMMUNITY ORGANIZATION | KATENGEZA COMMUNITY ORGANIZATION
NAME OF THE PROJECT : NONE
RECEIPTS ( NDALAMA ZOLOWA ) |  |  |  |  | 2019 |  | PAYMENTS ( NDALAMA ZOTULUKA ) |  |  | 2019
Date | Supllies | Qty | Unit Price | Value (MK) | Date | Received Amount | Date | Details | Amount | Personnel Costs | Production | Transport | Marketing | Indirect Costs | Running Balance
[6 empty] | MK |  |  | MK | MK | MK | MK | MK | MK | MK
2019-04-01 | Opening Balance | 1 | 1 | 0 |  | 0 |  |  | 0 | [5 empty] | 0
[9 empty] | 0 | [5 empty] | 0
2019-08-19 | Moringa Powder | 67 | 2000 | 134000 | 2019-08-20 | 11000 | 2019-03-13 | Moringa leaves purchase | 76000 |  | 76000 |  |  |  | -65000
2019-08-20 | Mvunguti Powder | 27 | 3000 | 81000 | 2019-08-27 | 11000 | 2019-03-13 | Transport of raw material and product to market | 75000 |  |  | 30000 |  |  | -84000
[5 empty] | 2019-09-05 | 50000 | 2019-03-17 | Milling | 25000 |  | 25000 |  |  |  | -59000
2019-08-27 | Mvunguti Powder | 50 | 3000 | 150000 | 2019-09-09 | 200000 | 2019-09-05 | Purchase of Bottles | 50000 |  | 50000 |  |  |  | 91000
2019-08-27 |  |  |  | 0 | 2019-09-17 | 100000 |  | Marketing( making of Lebels) | 35000 |  |  |  | 35000 |  | 156000
2019-09-17 | Moringa Powder | 80 | 2000 | 160000 | 2019-09-17 | 17500 | 2019-08-20 | Transport |  |  |  | 4000 |  |  | 169500
2019-09-17 | Mvunguti Powder | 97 | 3000 | 291000 |  |  |  | Mvunguti sauge fruit collection | 30000 |  | 30000 |  |  |  | 139500
[6 empty] | 30000 |  | Processing charge | 45000 |  | 45000 | 20000 |  |  | 104500
2019-11-01 | Mvunguti Powder | 100 | 3000 | 300000 | 2019-11-27 | 50000 |  | Milling charge | 26000 |  | 30000 |  |  |  | 124500
2019-11-01 | Gondolosi | 50 | 3000 | 150000 | Jan,19 | 180000 |  | Transport |  |  | 12000 |  |  |  | 292500
2019-11-01 | Lemongrass powder | 17 | 3000 | 51000 | 2020-01-20 | 300000 |  | Mondia White (Ngondolosi) purchase | 45000 |  | 45000 |  |  |  | 547500
|  |  |  | 0 | 2019-12-19 | 100000 |  | Transportation | 16000 |  |  | 16000 |  |  | 631500
|  |  |  | 0 | 2019-12-24 | 70000 |  | Milling charge | 13000 |  | 13000 |  |  |  | 688500
|  |  |  | 0 | 2020-01-25 | 100000 |  | Lemon Grass Collection/Purchase | 37000 | [5 empty] | 788500
2019-12-01 | Donation (Wellwisher) |  |  |  |  | 500000 |  | Milling charges | 12000 |  | 34000 |  |  |  | 1254500
[8 empty] | Transportation | 7000 |  |  | 7000 |  | 0 | 1247500
[8 empty] | Milling machine | 450000 |  | 450000 |  |  |  | 797500
[8 empty] | Transportation | 11000 |  |  | 11000 |  |  | 786500
[8 empty] | Communication | 41000 |  |  |  |  | 41000 | 745500
[8 empty] | Monthly earnings(wages) | 750000 | 750000 |  |  |  |  | -4500
[8 empty] | Bank Charges | 46200 |  |  |  |  | 46200 | -50700
|  |  |  | 1317000 |  | 1719500 |  |  | 1790200 | 750000 | 810000 | 88000 | 35000 | 41000 | -55200
[14 empty] | Closing Bal | -55200

## Sheet3
TIL-CB2-16-043-G |  | CASH SUMMARY | annex_5c
PROJECT NAME: | Strengthening Waste Management Systems in Blantyre City (SWAMS)
PERIOD OF REPORT: | June to July, 2016
MK
Opening Cash Book Balance (as per previous Bank Reconciliation Statement): |  |  | -8831.55
Add: Cash Received during the period:
| Funding Tranche |  | 12935171.5
| Interest received for the Period |  | 1457.12
Other Funds Deposits (that relates to grant e.g insurance claims)
Total Cash Received this period: |  |  | 12936628.62
Total Cash Available: |  |  | 12927797.07
Less: Expenses Incurred in this period:
| Total Expenses (same as that on exp. report) |  | 13097496.98
Total Expenses in this period |  |  | 13097496.98
Closing Cash Book Balance |  |  | -169699.91